## Proposed Product Backlog
Category | User Stories (Epics) | Assigned To
Gamer | <As a> gamer, <I want to> press START button <so that> I can start playing game | Everistus
| <As a> gamer, <I want to> look at the leaderboard <so that> I can see how my scores stack up | Everistus
| <As a> gamer, <I want to> click on the QUIT button <so that> I can exit the game | Everistus
| <As a> gamer, <I want to> move the spaceship using four arrow keys <so that> I can navigate the game scene | Everistus
| <As a> gamer, <I want to> shoot bullets when I press the SPACE bar <so that> I can kill enemies | Everistus
| <As a> gamer, <I want to> earn points for killing enemies <so that> I can increase my score | Everistus
| <As a> gamer, <I want to> collect powerups from the scene <so that> I can have an advantage against enemies | Everistus
| <As a> gamer, <I want to> be susceptible to damage <so that> I can lose a life when hit by the enemy or their droppings | Everistus
| <As a> gamer, <I want to> have protection when I respawn <so that> I can have time to re-coup and continue the wave | Everistus
| <As a> gamer, <I want to> have a health bar <so that> I can lose when it is depleted | Everistus
Bullet | <As a> bullet, <I want to> travel from the shooter's barrel vertically <so that> I can kill enemies as I hit them while on the move | Everistus
| <As a> bullet, <I want to> explode on impact <so that> I can deal damage to enemies. | Everistus
Bird | <As a> Bird, <I want to> appear during a wave and take formation <so that> I can make it harder for a player to get past me | Everistus
| <As a> Bird, <I want to> move randomly <so that> the gamer cannot easily kill me | Everistus
| <As a> Bird, <I want to> release lethal droppings <so that> I can damage the gamer's spaceship | Everistus
Asteroid | <As an> Asteroid, <I want to> appear during a wave and bounce around the screen <so that> it is harder for a player to predict my movement | Everistus
| <As an> Asteroid, <I want to> move randomly and be harder to destroy <so that> the gamer cannot easily kill me | Everistus
| <As an> Asteroid, <I want to> spawn more asteroids when I am destroyed <so that> I can make the wave harder for the player | Everistus

## Sprint1
Sprint Backlog: Sprint 1
Category | EPICs (User Stories) | ID | Child User Stories | Assigned To | Status | Notes
Gamer | As a gamer, I want to move the shooter using four arrow keys so that I can navigate the shooter on the game scene | 1 | As a gamer, I want to move the shooter using 4 arrow keys so that the shooter can navigate the game scene | John | completed
|  | 2 | As a gamer, I want to move the shooter without leaving the game scene so that the shooter does not disappear from the screen | John | completed
Missile | As a missile, I want to travel from the shooter's barrel to the mouse press location so that I can kill enemies as I hit them while on the move | 3 | As a missile, I want to travel along the line from the shooter to the mouse press location so that I can trace the target | Mary | completed
|  | 4 | As a missile, I want to hit enemies along the travel path so that I can kill enemies | Mary | in progress | forwarded to Sprint 2
Gamer | <As a> new gamer, <I want to> sign up an account <so that> I can have access to games available. | 5 | As a new gamer, I want to sign up an account so that I can be a register user. | Bill | completed
|  | 6 | As a new gamer, I want to sign up an account so that I can sign in with the account credentials. | Bill | completed
Each child user story must have all of 3 clauses too: <As a> … <I want to> … <so that>
You are allowed to introduce a new EPIC that is not in the proposed Product Backlog. In "Notes" column, remark it as a new EPIC. However, do not edit the original Product Backlog.

## Sprint1 Acceptance
Child User Story ID | Acceptance Criteria | created by (member) | verified by (test engineer) | tested by (test engineer) | Result | Note
1 | The shooter moves to the right by 10 pixels with the right arrow key press | John | Bill | Bill | pass
| The shooter moves to the left by 10 pixels with the left arrow key press | John | Bill | Bill | pass
| The shooter moves upwards by 10 pixels with the up arrow key press | John | Bill | Bill | pass
| The shooter moves downwards by 10 pixels with the down arrow key press | John | Bill | Bill | pass
| As lef key is pressed 20 times, the shooter crosses from right edge to left edge of screen | John | Bill | Bill | fail | incorrect screen size may be used
| As right key is pressed 20 times, the shooter crosses horizontally from right edge to left edge of the screen | John | Bill | Bill | fail | incorrect screen size may be used
| For each of 4 arrow keys, the shooter moves continuously as the key is kept pressing | John | Bill | Bill | pass
2 | At the right edge, the shooter does not move to the right arrow key press | John | Bill | Bill | pass
| At the left edge, the shooter does not move to the left arrow key press | John | Bill | Bill | pass
| At the top edge, the shooter does not move to the up arrow key press | John | Bill | Bill | pass
| At the bottom edge, the shooter does not move to the down arrow key press | John | Bill | Bill | pass
| At the four corners of the game scene, the shooter stays inside the scene after pressing arrow keys | John | Bill | Bill | pass
3 | The missile launches always from the shoot's barrel as the shooter changes its location | Mary | Bill | Bill | pass
| The missile stops at the mouse press location. | Mary | Bill | Bill | pass
| The missile kills enemies as it hits them. | Mary | Bill | Bill | pass
5 | As a new user signs up, the user record is created in the profile database. | Bill | Bill | Bill | pass
| The new user record include username and password. | Bill | Bill | Bill | pass
| The user password is encripted using SHA256 algorithm | Bill | Bill | Bill | fail | stored password is not encrypted
| If the reqeusted username for a new account is already used, a signup error message shows up | Bill | Bill | Bill | pass
| If the new password to register is less than 6 characters long, an error message shows up | Bill | Bill | Bill | pass
More than 1 acceptance criteria per child user story is strictly required. If you cannot find multiple acceptance criteria for a child user story, you need to redesign the child user story. It is too small. Acceptance criterion must NOT be mere repetition of child user story. It must contain more info for proper testing.

## Finalized Product Backlog
ALL Completed Child User Stories Based on the Submitted Program.
Category | Child User Stories | Assigned To | Status | Notes